## Sheet1
Communal issue | Location | Action Taken | Date | Follow Up Action Required | Department | Follow up date | Updates
Pink Sack Delivery | All Areas | Meeting with Suez carried out Wednesday | 2026-07-29 | Andy from Suez emailed NR and gave his personal email for residents to contact him regarding pink sacks deliveries. Follow-up topic for future meetings Creation of a joint Suez/SEH pink bag delivery alert process for the blocks. | Estates/Suez |  | Completed - andy.mcphee@suez.com “When the different properties require pink sack to come through me, I can arrange deliveries”.
Communal Lounge and Chairs | Bishop | Cleaning has taken place. Staining and wear and tear visible. | 2026-07-24 | SA confirmed that replacement is not in budget. | Estates |  | Completed
Communal carpets | Adams | Cleaning has taken place. Staining and wear and tear visible. | 2026-07-24 | SA confirmed that replacement is not in budget. | Estates |  | Completed
Chiltern 140L Bins | Chiltern, Malvern, Quantock, Kingfisher, Sandpiper | Agreed delivery date Monday 27th July | 2026-07-24 | No | Suez | 2026-08-11 | Completed - Email received from Andy Suez confirming 1,100 ltr bins delivered and food waste bins to Kingfisher and Sandpiper. These bins will be monitored for ASB.
Blocked pull cord/Instakil/Door magnets | Adams |  | 2026-07-24 | Bins have been moved and pullcord is accessible. Signage created. | SEPS/Instakill | 2026-09-12 | Completed - email received from Melanie with pictures of changes to bin room.
Kingfisher Hall cleaning | Kingfisher | Provide cleaning materials broom mop etc. | 2026-07-24 | NR emailed SA on 13/08/2026 requesting large broom for Kingfisher. As per MM request. | Estates | 2026-08-13 | Outstanding - NR has not received an update.
Bishop House | Bishop | Area cleared of branches | 2026-07-27 | No | Estates GM | 2026-07-27 | Completed
Atrium Riverstone faeces | Riverstone | Caretakers say this has been done | 2026-07-14 | I will attend site to double check this week W/C27/07/2026 | Estates | 2026-07-27 | Completed
Broken Lift | Malvern | Waiting for part. | 2026-07-24 | Repaired on 29/07/2026. | SEPS | 2026-07-29 | Completed
Broken Lift | Bishop | Waiting for update about repair and lift surveys of SEH properties. |  | Follow-up topics for future meetings Results of lift surveys of SEH properties and any plans of action. | Dave Campling | 2026-09-07 | Outstanding - NR sent email to DC on 07/09/2026
Shed at Riverstone | Riverstone | Emailed tenancy to find out who the shed belongs to. | 2026-07-27 | NR sent an email to tenancy team to check deadline date for shed claim. | Estates | 2026-09-04 | Outstanding - NR sent email to tenancy officer on 04/09/2026
Riverstone rubbish sheds | Riverstone | Compost bins dumped it is attracting vermin. | 2026-07-27 | SA to visit and order Instakil to attend. Waiting for potting shed to be removed and this waste will be removed at the same time. | Instakil/Estates |  | Outstanding - NR has not received an update.
Bishop House Canopy removal | Bishop | Will be removed by SEPS W/C 03/08 | 2026-07-24 | Job number 7325399/1. SEPS could not remove the canopy as it was electrical. NR emailed JN to find out whether Axis electricians had been asked to make it safe for removal. | SEPS/Axis | 2026-09-15 | Outstanding - NR has not received an update. Received email from resident Axis have made canopy electrics safe. Email to Stewart to send SEPS to remove it.
Adams Elms overgrown shrubs | Adams | Bushes cut back by GM team | 2026-07-27 | No | GM |  | Completed
Christchurch Bulk | Christchurch | Bulk colected | 2026-07-24 | No | Estates |  | Completed
Adams Elms windows by pond | Adams | we are looking into whether this can be done |  | Email received from resident thanking us for completing the work. | Axis | Window cleaners need to be informed and do HSE check. | Outstanding - NR has not received an update.
Bishops House blocked drain | Bishop | SA to contact Paris to check blocked drain resolved. |  | Drains were cleaned by Axis. We will keep record of incidents on action log and CJ will review. |  |  | Completed
Adams Elm drain clearance and flooding | Adams | SA to contact Paris to check blocked drain resolved. | 2026-07-24 | Drains were cleaned by Axis. We will keep record of incidents on action log and CJ will review. | Axis | 2026-08-11 | Completed
Adams Elm House LED lights | Adams | Several LED lights out in communal areas including stairwells by office and at back door leading to garden. | 2026-07-24 | JN to check progress. | Axis |  | Outstanding - NR has not received an update.
Adams Elm House Pond | Adams | Pond cleaning and mainteance. | 2026-07-24 | Axis attended to fix the pump on Monday 3rd August 2026. The pump is broken and needs to replaced. | SEPS | 2026-09-04 | Outstanding - NR sent email on 4th September 2026 to Paul Longman asking for an update.
Adams Elm House Leak first floor ceiling | Adams | Leak from second floor radiator pipe. BA to contact Sure serve to check whether this is coming from the radiator pipes. | 2026-08-20 | BA asked Sure Serve to investigate. They are due at property on 8th September 2026. | BA/Sure serve |  | Outstanding - waiting for update from Sure serve
Riverstone No Parking Sign | Riverstone | JN of Axis agreed to liaise with tenancy officer and put up the sign. | 2026-08-20 | No | Axis |  | Completed
Sandpiper and Kingfisher garden bench | Sandpiper/Kingfisher | Garden bench damaged by lawnmower. Residents to apply for money from the Community Fund for new furniture. | 2026-07-24 | CC/MM have purchased their own tables and chairs, and Sandpiper were awarded £250 from the community fund. | Resident Engagement | 2026-09-04 | Partial - community fund monies to be collected. Email sent to advise collection.
Sandpiper drain cover | Sandpiper | Replacement drain cover job no C00824984 | 2026-07-24 | JN has job number and is checking progress. | Axis | 2026-09-16 | Outstanding - email received from the resident saying job to replace drain cover is outstanding.
Dog fouling | Neil Armstrong Way/Scott House | Karen/SG to discuss options of signage or use the funds available for planters. | 2026-07-24 | Follow-up topic for future meetings Anti fly-tipping survey and use of planters for green areas to discourage it. Scott House information book trial and suggested use of noticeboards. | Resident Engagement/Estates |  | Outstanding - NR has not received an update.
Solar panels | All Areas | SA/SG to discuss energy sustainability options for sheltered housing properties. | 2026-08-20 | Follow-up topic for future meetings Energy use and sustainability | Resident Engagement/Estates |  | Outstanding - NR has not received an update.
Overgrown front garden | Adams | SA has added to the job list. This is a low risk job as SEH are currently working through the high risk tree survey list. | 2026-07-24 |  | Estates |  | Outstanding - NR has not received an update.
Uneven path and ivy | Bishop | SA advised that to even out the path would be a capital project that isn’t scheduled in the budget. | 24/07/202 | No | Estates |  | Completed
Back door step faeces clean and fire door security measures | Adams | The fire safety officer asked for more information by email. To investigate possible key entry of back door to stop non residents opening this door to let unauthorised people into sheltered property. | 2026-07-24 | JM to send pictures to SG. Estates to jet wash back step. | Resident Engagement/Fire Safety Officer |  | Outstanding - NR has not received an update.
Damp wall right of front door | Bishop | Resident believed that wallpaper repair was completed by contractor without treating the wall first as staining has re-appeared. | 2026-08-20 |  | Axis |  | Outstanding - NR has not received an update.
Repainting of disabled bays | Longbow | Residents to report and provide photos of bays. | 2026-08-20 | BA has taken pictures and sent to Axis. | Axis